## Slide 1: PROJECT PLAN INFLUENZA SEASON
By Ivonne Aspilcueta

## Slide 2: PROJECT OVERVIEW
Goal: To help the medical staffing agency that provides temporary workers to clinics and hospitals on planning for influenza season, and a time when additional staff are in high demand.
Motivation: Hospitals and clinics need additional staff to adequately treat patients, particularly those in vulnerable populations, who develop serious complications and end up in the hospital.
Objective: To Determine the time and quantity of temporary medical staff, to each state.
Scope: The agency covers all hospitals in each of the 50 states of the United States, and the project will plan for the upcoming influenza season.

## Slide 3: Stakeholder Identification
Medical agency frontline staff (nurses, physician assistants, doctors)
Hospitals and clinics using agency services
Staffing agency administrators
Influenza Patients

## Slide 4: STAKEHOLDER COMMUNICATION
Planning and general meetings will be schedule with hospitals and clinincs, Medical agency frontline staff and Staffing Agency Administrators to set up goals on the progress of the project, data insights, clarifications, selecting items to prioritize and feedbacks.
MEETINGS
EMAILS
Email communication for progress, updates, reports and timely will be sent to stakeholders to use the information to build strategies, and any urgent information during the process of the project.
CALLS
CONTINGENCY PLAN
Conference calls will be taken place for discussions and adressing any questions or concerns, and introduce any new news (New personnel, changes).
Urgent communication for unexpected changes or issues with administrators and management to overcome challenges duringthe project.

## Slide 5
WEEK | MILESTONE | ACTIVITIES
PHASE ONE |  | 
Week 1 | Start with Business requirements. Designing a Data Research Project. | Create a list of data questions for analysis, design the project research by formulating research hypothesis.
Week 2 | Sourcing the Right Data. Data Profiling and Integrity. | Data collection, cleaning data, work on EDA. Explain data limitations. Information on data types, data integrity issues (accuracy and consistency).
Week 3 | Data Quality Measures. Data Transformation & Integration. | Transform and integrate data sources, implement additional data quality measures to completeness, uniqueness, and timeless.
Week 4 | Conduct Statistical Analyses. Statistical Hypothesis Testing. Consolidate Analytical Insights. | Create statistical analysis based on the hypothesis and interpret results, share with peer for feedback. Create report consolidating the findings.
PHASE TWO |  | 
Week 5 | Data Visualization Composition and comparison Charts Forecasting | Visualizing data insights. Create forecasting to predict any behavior or needs to develop an action plan.
Week 6 | Statistical Visualization Spatial Analysis | Use the SCR format for data visualization, looking for trends, challenges, create visualization to look at the correlation between variables.
Week 7 | Textual Analysis Storytelling | Create a qualitative data and a narrative to communicate findings and insights, recommendations.
Week 8 | Presentation | Publish analysis in Tableau Storyboard and present to Stakeholders.

## Slide 6: Initial Report Data Visualizations Presentation DELIVERABLES
Create data visualization in Tableau to be available to stakeholders in real time
Final presentation with recommendations.
A written report with our conclusions, insights and methods to prepare the future presentation

## Slide 7: Hypotheses
If we provide educational material to increase knowledge to change the perceptions towards influenza, then we increase the healthy and preventive behavioral practices.
If some states have the higher vulnerable population for influenza, then more temporary medical staff is needed than other states.
If the vulnerable population (65+ and 5 under Age) are low income, then they are a mortality rate group.
If temporary staff get the virus then they need to have replacemnet as a backup.

## Slide 8: Data Wishlist
Education on the states with the highly vulnerable population.
Vaccination to people ages 65 and older and people with health condition.
Mortality rate of the vulnerable population with low income.

## Slide 9: THANK YOU